## Meadowlake
SIX YEAR CAPITAL IMPROVEMENT PROGRAM (CIP) WORKSHEET
Airport Name | Meadow Lake Airport (00V) |  |  | CIP Update
Airport Manager | Dave Elliott |  |  | Airport Engineer/ Consultant: Airport Development Group
Airport Sponsor | Meadow Lake Airport Assn. |  |  | ADO Contact: Linda Bruce
Address | 13625 Judge Orr Road, Peyton, CO 80831
Phone | 719-683-7736 |  |  | Cell: 719-339-0928
Project Description | FAA State Apport. | GA Entitlement | State | Local | Total | Comments
Historical Year - 2008
Land acquisition | 500000 |  | 13157 | 13157 | 526314
Beacon |  |  | 8000 | 2000 | 10000
Business Plan |  |  | 100000 | 25000 | 125000
Land Reimbursement |  | 150000 | 3948 | 3948 | 157896
Total Year 2008 | 500000 | 150000 | 125105 | 44105 | 819210
Year - 2009
Runway 15-33 Pavement and Lighting Rehab |  |  | 292052 | 73013 | 365065
Purchase Johnston Property and Hangar |  |  | 500000 |  | 500000 | New SIB Loan
Land Reimbursement |  | 150000 | 3948 | 3948 | 157896
Total Year 2009 | 0 | 150000 | 796000 | 76961 | 1022961
Year - 2010
SRE/Equipment Building/Airport Office |  | 150000 | 200000 | 50000 | 400000
Remove Hangar Restaurant | 71250 |  | 1875 | 1875 | 75000
Total Year 2010 | 71250 | 150000 | 201875 | 51875 | 475000
Year - 2011
Fuel Storage and Dispensing |  | 150000 | 50000 | 50000 | 250000
Land Reimbursement | 300000 |  | 7895 | 7895 | 315790
Total Year 2011 | 300000 | 150000 | 57895 | 57895 | 565790
Year 2012
EA for Replacement Runway | 332500 |  | 8750 | 8750 | 350000
Land reimbursement | 300000 | 150000 | 11842 | 11842 | 473684
Totals - Year 2012 | 632500 | 150000 | 20592 | 20592 | 823684
Year 2013 |  |  |  |  | 0
Preliminary Design Engineering for Replacement Runway |  | 150000 | 3948 | 3948 | 157896
Totals - Year 2013 | 0 | 150000 | 3948 | 3948 | 157896
Year 2014
Replacement RWY Construction Ph. 1 | 2500000 | 150000 | 69737 | 69737 | 2789474
Apron Construction | 600000 |  | 15790 | 15790 | 631580
TOTALS - Year 2014 | 3100000 | 150000 | 85527 | 85527 | 3421054
TOTAL 7 YEAR COSTS | 4603750 | 1050000 | 1290942 | 340903 | 7285595
NPIAS projects for long-term completion - by priority
AWOS (2009) |  |  |  |  | 130000
ALP Update (2010) |  |  |  |  | 60000
Security Improvements Phase1/Wildlife Fencing (2010) |  |  |  |  | 1000000
Runway Sweeper (2011) |  |  |  |  | 157896
Construct New X-Wind Runway and Drainage Impr, (2012) |  |  |  |  | 3000000
Construct New Additional Aircraft Parking Apron (2014-15) |  |  |  |  | 1500000
Realign and Extend Primary RWY and TWY (2014-15) |  |  |  |  | 6500000
Constuct New Parallel Runway (2020) |  |  |  |  | 1500000